## Sheet1
CLIENT: |  | EMF CHANDLER, LLC
6900 DALLAS PARKWAY, 3RD FLOOR
PLANO, TX 75204
ATTN: |  | ANGELA HILL
CONTRACT #: |  | 2004E02S
DATE: |  | 09.03.24
SIGNAGE PROGRAM: |  | ENCORE NOVO
SIGNAGE ITEMS DELETED FROM CONTRACT: |  |  |  | -931
A. | -1 | CUSTOM HANDICAP PARKING SIGNS ON POLE W/BASEPLATE | 795 | -795
(LEASING EXTERIOR)
B. | -1 | LEASING OFFICE ID W/BACKER (LEASING INTERIOR) | 78 | -78
(CHANGED TO VINYL)
C. | -1 | UTILITY ROOM (BUILDING C - LEVEL 4) | 58 | -58
SIGN CHANGES / ADDITIONS DURING BOOK REVIEW PHASE: |  |  |  | 2567
A. | 1 | CHANGED LEASING ID TO LEASING DOOR DECAL | 189 | 189
B. | 4 | BUILDING IDS (SITE SIGNAGE) (ADDED PER FM) | 235 | 940
C. | 1 | ELECTRICAL (BUILDING A - LEVEL 1) | 48 | 48
D. | 1 | FACP (BUILDING A - LEVEL 1) (NOT ON PLAN SET) | 110 | 110
E. | 1 | MAINTENANCE (BUILDING B - LEVEL 1) | 48 | 48
F. | 3 | ELECTRICAL (BUILDING B - LEVEL 1) | 48 | 144
G. | 1 | ERRC ID (BUILDING B - LEVEL 1) (ADDED BY FM) | 58 | 58
H. | 1 | IT ID (BUILDING B - LEVEL 2) | 58 | 58
I. | 1 | ELECTRICAL (BUILDING C - LEVEL 1) | 48 | 48
J. | 4 | 911 DIRECTIONAL - FENCE MOUNT (AMENITY) | 165 | 660
K. | 1 | CHEMICAL WARNING (MOUNTED ON CHEMICAL STORAGE DOOR) | 88 | 88
(AMENITY)
L. | 1 | OZONE SIGN (AMENITY) (ADDED BY INSPECTORS) | 88 | 88
M. | 1 | CPR PANEL SIGN - FENCE MOUNT (AMENITY) | 88 | 88
SIGN CHANGES / ADDITIONS DURING INSTALLATION PHASE: |  |  |  | 6036.1
A. | 16 | AREA OF REFUGE (ALL BLDGS PER FM / JOB SUP) | 98 | 1568
(NOT INDICATED ON ORIGINAL PLAN SET)
B. | 1 | MAIL ROOM GRAPHICS (ADDED BY RYAN WILLIAMS/MIGUEL ORTEGA) ) | 950 | 950
C. | 15 | EXIT ID (PER FM - ADDED BY RYAN WILLIAMS) ADD PANEL TO | 38 | 570
EXISTING STAIR SIGNS PER FM REQUEST
D. | 1 | FACP (BUILDING A - LEVEL 1) | 110 | 110
(UPGRADED TO DIAMOND GRADE) (PER FIRE CODE)
E. | 1 | BUILDING ADDRESS DIMENSIONAL NUMERALS (MIGUEL ORTEGA) | 710 | 710
(MADE TEMP AND PERM)
F. | 1 | TEMP PACKAGE FOR BUILDING A & C (ADDED BY RUAN WILLIAMS) | 350 | 350
G. | 4 | GATE SIGNS - SWiNG GATE (ADDED BY MIGUEL ORTEGA / RYAN QILLIAMS) | 185 | 740
(SITE NOT READY FOR PERMANENT SIGNS)
H. | 1 | SHIPPING / HANDLING OF ADDED SIGNAGE | 1038.1 | 1038.1
(OVERNIGHT CHARGES FOR ADD-ON SIGNS NEEDED ASAP)
SUBTOTAL |  |  |  | 7672.1
SALES TAX: |  |  |  | 632.9483
TOTAL ADDED SIGNAGE |  |  |  | 8305.0482
ADDITIONAL INSTALLATION: TEMP SIGNAGE, ADD-ON SIGNAGE, AND BEING CALLED OUT TO TROUBLE SHOOT POWER. |  |  |  | 3450
DISCOVERED ELECTICAL HAD NOT BEEN CONNECTED. REQUIRED BIG CRANE SERVICE.
PERMIT FEES (BILLED AT COST): |  |  |  | 336
TOTAL AMOUNT TO BILL ABOVE AND BEYOND: |  |  |  | 12091.0482